# KOSMTP — RECOMMENDED APPROACH FOR MMB PRESENTATION

Purpose: secure MMB's strategic guidance and a defined next-step pathway for Vijaydurg site pre-feasibility and DPR development. The first meeting should not be presented as a request for immediate land allotment, funding sanction or final PPP approval.

# 1. Position the proposal correctly

Present KOSMTP as a Maharashtra maritime capability project built around skills and qualifications plus four market-facing facilities: the Vijaydurg Maritime Living Lab and Sea-Validation Facility; the Marine Asset Integrity and Inspection Services Centre; the Applied Research and Maritime Data Centre; and the Marine Robotics Assembly, Repair and MRO Cluster. The central message is a learn–research–assemble–test–validate–deploy–support ecosystem.

# 2. The first ask to MMB

Ask for strategic feedback; MMB's view on Vijaydurg as a candidate location; a nodal technical interface; guidance for site pre-feasibility and data review; the DPR/PPP pathway; and a second-stage technical consultation with port, hydrographic, engineering and planning officials.

# 3. What not to lead with

Do not open with investment figures, a 25-acre request, defence applications or international certification terminology. Explain these only after MMB understands the maritime-development logic. Do not present preliminary NSQF levels, standards benchmarking or scheme convergence as already approved.

# 4. Recommended meeting sequence

Use 5 minutes for the Maharashtra problem and Vijaydurg opportunity; 10 minutes for the four-pillar model; 5 minutes for skills and research; 5 minutes for autonomous marine systems and test validation; and 10–15 minutes for MMB's questions. End with four requests: strategic feedback, location pre-feasibility guidance, nodal coordination and the DPR pathway.

# 5. Phase-0 proof strategy

Recommend a 12-month pilot before major campus CAPEX. The pilot should complete paid inspection assignments, operate selected short courses, mobilise initial MRO capability, establish the maritime data architecture, complete a controlled Vijaydurg technology demonstration and secure anchor-partner letters for the DPR.

# 6. My recommended next document set

After the CEO meeting, prepare: a 2-page Executive Brief; a 12-slide MMB presentation; a Vijaydurg Site Pre-Feasibility Terms of Reference; and a DPR structure covering CAPEX, OPEX, land/waterfront, regulatory, research, qualification and PPP workstreams. This is more credible than submitting a full DPR before MMB indicates that the location and project framing merit detailed examination.

# 7. Recommended 12-slide CEO presentation

| Slide | Title |
| --- | --- |
| 1 | The opportunity |
| 2 | Why KOSMTP |
| 3 | Why Vijaydurg |
| 4 | Four strategic operating facilities |
| 5 | Underwater skills architecture |
| 6 | Marine Robotics Assembly, Repair and MRO |
| 7 | Applied Research and Maritime Data Centre |
| 8 | Asset Integrity and Inspection Services |
| 9 | Maritime Living Lab and Sea-Validation Facility |
| 10 | Phased implementation |
| 11 | Maharashtra impact |
| 12 | Our request to MMB |